## Engagement Summary
Engagement Costs |  |  | Profit Metrics
Total Estimated Effort | 100170.5 |  | Total Cost | 1600
Total Fees | 0 |  | Profit Margin | 98.4%
Grand Total | 100170.5
Role | Total Hours | Total Cost
Business Development Manager | 0 | 0
Content Writer | 0 | 0
Creative Director | 0 | 0
Data Analyst / Scientist | 0 | 0
Design Thinker/Facilitator | 0 | 0
Graphic Designer | 0 | 0
Innovation Coach / Mentor | 0 | 0
Innovation Strategist/Consultant | 0 | 0
Junior Software Engineer | 156 | 35100
Principal | 8 | 3200
Project Manager | 0 | 0
Research Analyst | 0 | 0
Senior Software Engineer | 56 | 15400
UI / UX Designer

## Project Effort
Total Estimated Effort (Hrs) | 236
Total Estimated Effort Fee | 100170.5
Total Cost | 1600
Profit Margin | 98.4%
Task | Description | Role | Estimated Hours | Rate | Total Fee | Total Cost
Overall Strategy | Project PM & Leadership | Principal | 8 | 400 | 3200 | 1600
Dealer Map Integration
Custom App | Dealer / ThinkBIG map accessible somewhere constant within UI via icon. Clicking on icon pops up map showing dealer territories with dealer logos. User zooms, navigates, taps on state or area of dealer, which bring up a dialog box with dealer info, associated ThinkBIG school and contact information for both? | UI / UX Designer | 10 | 175 | 1750 | 800
| Display Map with dealer and ThinkBig pins with navigation controls (zoom, pan) | Senior Software Engineer | 40 | 275 | 11000 | 4000
| Highlight a specific dealer or ThinkBig school showing their details (locations, services, programs, links, etc.) | Junior Software Engineer | 24 | 225 | 5400 | 1200
| Filter map by state/zip code (from url param and/or clicking map) to show closest dealer and ThinkBig program with details | Junior Software Engineer | 24 | 225 | 5400 | 1200
Platform changes | Update Momentify/Explorer to allow passing url params to web embeds (to pass zip code to embedded app for auto-filtering) | Junior Software Engineer | 16 | 225 | 3600 | 800
No backend needed to store data
Interactive Pin Experience
| Setup new moment + 16:9 display companion. Background is NA Dealer Map with a counter on each dealer logo. On iPad as a dealer pin is exchanged with attendee (from their state), the count for said dealer reduced from 10 to 0. Pin exchangee must walk thru template in order to complete pin exchange? | UI / UX Designer | 6 | 175 | 1050 | 480
Pin admin app | Manage exchange "projects" (name/date of the event) | Senior Software Engineer | 16 | 275 | 4400 | 1600
| Manage dealers list and initialize counts | Junior Software Engineer | 16 | 225 | 3600 | 800
| Attendee mode with basic registration questions (name, zip, etc.) | Junior Software Engineer | 16 | 225 | 3600 | 800
| Order dealers by closest to zip code showing remaining pin counts | Junior Software Engineer | 16 | 225 | 3600 | 800
| Decrement dealer pin count | Junior Software Engineer | 4 | 225 | 900 | 200
Display app | Display map with dealers pinned on map | Junior Software Engineer | 24 | 225 | 5400 | 1200
| List of all dealers with their count of pins remaining / swapped | Junior Software Engineer | 16 | 225 | 3600 | 800
26150
|  |  |  | 33% off | 17520.5

## Fees
Total Fees |  | 0
Item | Type | Description | URL | Cost | Quantity | Markup | Total Cost
The Trade Group | Vendor | Booth Design & Fabrication |  |  | 1 | 20
The Trade Group | Vendor | Booth Shipping |  |  | 1 | 20
The Trade Group | Vendor | Booth Storage |  |  | 1 | 20

## REF Rate Card (hidden)
Role | Description | Billable Rate | Cost Rate
Business Development Manager | Identifying and pursuing new business opportunities. | 175 | 110
Content Writer | Crafting content and copy for marketing, training, and other communications purposes. | 125 | 65
Creative Director |  | 250 | 110
Data Analyst / Scientist | Analyzing data to derive insights for innovation. | 175 | 85
Design Thinker/Facilitator | Leading design thinking workshops and innovation sessions. | 250 | 100
Graphic Designer | Creating visual assets and branding materials. | 150 | 65
Innovation Coach / Mentor | Providing guidance and mentorship to individuals and/or teams. | 300 | 100
Innovation Strategist/Consultant | Provide strategic guidance for innovation activities. | 350 | 150
Junior Software Engineer | Building software or technology solutions for innovation projects (Junior Level). | 225 | 50
Principal | ENTEVATE Leadership | 400 | 200
Project Manager | Overseeing the planning and execution of projects. | 175 | 110
Research Analyst | Conducting market research and trend analysis. | 125 | 80
Senior Software Engineer | Building software or technology solutions for innovation projects (Senior Level). | 275 | 100
UI / UX Designer | Designing user-centric product and services experiences. | 175 | 80